## Summary
HMS_WPF - Issue and Feature Log
Read-only code analysis of the HMS_WPF solution (Pharma.App / Pharma.Core / Pharma.Data). No code was changed.
Source: analysis session 28 Jul 2026. Evidence column cites the file and line each finding was read from.
How to use this workbook
Yellow cells are yours to fill in | Priority, Severity / Criticality, Status, Owner, Target and Notes on both sheets.
'Suggested' column | My suggestion only, from the code analysis. It is deliberately kept separate so it never overwrites your call.
Priority - Bugs sheet | P1 / P2 / P3 (dropdown provided)
Priority - Features sheet | C1 / C2 (dropdown provided)
Status - both sheets | Open / In Progress / Fixed / Deferred / Won't Do (dropdown provided)
Counts below | Live formulas over the Priority column - they update as soon as you fill it in.
Example of a completed row (for format only - not a real finding):
ID | Priority | Severity | Status | Owner | Target | Notes
B1 | P1 | Critical | In Progress | Srini | Sprint 1 | Switch to SQLite Online Backup API
Bugs by priority |  |  | Features by priority
P1 | 0 |  | C1 | 0
P2 | 0 |  | C2 | 0
P3 | 0 |  | Unset | 13
Unset | 14 |  | Total logged | 13
Total logged | 14

## Bugs
ID | Area | Issue | Why it matters | Evidence (file:line) | Suggested | Release | Priority | Severity | Status | Owner | Target | Notes
B1 | Backup / DR | Backup copies a live SQLite file with File.Copy | No SQLite backup API, no VACUUM INTO, no -wal/-shm or journal handling. A copy taken mid-transaction can be torn. This is the clinic's only disaster-recovery path. | src/Pharma.Data/DbBootstrapper.cs:151, :183 | P5 | 2
B2 | Backup / DR | No way to restore from a backup | Backups are written and pruned, but recovery is only possible by manually copying files outside the app. Verified absent from the whole codebase. | (absent - no restore code anywhere) | P5 | 2
B3 | Reports / Money | Consultation fees totalled by visit date, not payment date | Visit.FeePaidOn is recorded and printed on receipts but never used in any report. A fee collected on a later day lands in the earlier day's takings, so the till will not reconcile. | src/Pharma.App/ViewModels/ReportsViewModel.cs:178 | P2 | 1
B4 | Reliability / UX | Background failures are invisible to the user | Forget() logs the exception but shows nothing on screen. A failed stock re-allocation silently leaves a stale quantity on a bill line; a failed history load leaves stale data displayed. | src/Pharma.Data/AppLog.cs:283 | P2 | 2
B5 | Patients / Perf | Phone lookup loads every patient and can match the wrong family | GetPatientsByPhoneAsync reads all patients into memory, then suffix-matches in both directions, so a stored 6-digit number matches a 10-digit search. | src/Pharma.Data/OpdService.cs:62 | P3 | 2
B6 | Costing | Dead ternary in EffectivePackCost - both branches identical | Reads 'QtyOnHand > 0 ? PurchaseRate : PurchaseRate'. The intended logic appears to have been lost, so free-goods/margin figures derived from it are suspect. | src/Pharma.Core/Entities.cs:297 | P3 | 2
B7 | OPD | Token allocation has no transaction or unique constraint | Token is Max(TokenNo)+1 with no unique index on (date, token), so duplicate tokens are possible. Low risk while the app is single-user on one PC. | src/Pharma.Data/OpdService.cs:265 | P2 | 1
B8 | Inventory | Stock can be received with an expiry date in the past | Neither ReceiveStockAsync nor QuickAddStockAsync validates expiry. Expired batches enter the shelf, then are silently excluded from allocation - invisible dead stock with no warning. | src/Pharma.Data/PharmacyService.cs:260, :430 | P3 | 1
B9 | Counter | Sale does not re-check batch expiry at save time | SaveSaleAsync re-validates quantity but not IsExpired, so a bill line prepared before midnight can be saved after the batch has expired. | src/Pharma.Data/PharmacyService.cs:703 | P3 | 2
B10 | Patients / Validation | Age and phone accept invalid values | int.TryParse silently yields 0 for non-numeric age, and negative ages are stored unvalidated. Phone is free text with no format check or normalisation. | src/Pharma.App/ViewModels/PatientsViewModel.cs:191 | P3 | 2
B11 | Counter / Perf | Product lookup by Id loads up to 1000 rows | Both the prescription load and the line re-allocation call SearchProductsAsync(null, 1000) and then filter in memory to find a single product by Id. | src/Pharma.App/ViewModels/SaleViewModel.cs:266, :546 | P3 | 2
B12 | Inventory | Repack and adjust operate on soft-deleted batches | RepackAsync, PreviewRepackAsync and AdjustStockAsync do not filter IsDeleted, so deleted batches get recounted and adjusted. | src/Pharma.Data/PharmacyService.cs:563, :599, :384 | P3 | 2
B13 | Reports | Stock register includes batches of soft-deleted products | GetAllBatchesAsync filters deleted batches but not batches whose parent product has been deleted. | src/Pharma.Data/PharmacyService.cs:241 | P3 | 2
B14 | OPD | No visit status transition rules | SetStatusAsync accepts any status change, so a Completed or Cancelled visit can be moved back to Booked. | src/Pharma.Data/OpdService.cs:290 | P3 | 1

## Features
ID | Area | Feature | Why / value | Evidence (file:line) | Suggested | Release | Priority | Criticality | Status | Owner | Target | Notes
F1 | Counter / Money | Sales return, refund and bill cancellation | SaleStatus.Returned and .Cancelled exist and both reports already filter on them, but no code path ever sets them. A wrong bill is permanent and returned medicine cannot go back on the shelf. Half-built. | src/Pharma.Core/Enums.cs:98; ReportsViewModel.cs:158, :204 | C1 | 2
F2 | Backup / DR | Restore from backup inside the app | Pairs with B1/B2. Backups are useless to a clinic that cannot restore them without help. | src/Pharma.Data/DbBootstrapper.cs | C1 | 2
F3 | Security | Authentication and roles | No login of any kind. Anyone at the PC can view, edit and delete patient records, reprice stock and adjust quantities. Audit fields capture only the Windows username (Environment.UserName). | (absent); audit fields at Entities.cs:377, :543 | C1 | 2
F4 | Counter / Money | Edit or void a saved bill | There is no correction path once a bill is saved - only a fresh bill can be raised. | src/Pharma.Data/PharmacyService.cs:662 | C1 | 2
F5 | Counter | Discounts at the counter | SaleRow.DiscountPercent and the whole calculation chain support discounts, but it is pinned to NoDiscount = 0 and there is no input in the UI. Half-built. | src/Pharma.App/ViewModels/SaleViewModel.cs:86 | C2 | 2
F6 | Security | Database encryption at rest | Patient records sit in a plain, unencrypted SQLite file under C:\HMS\DB that can be copied off the machine wholesale. | src/Pharma.Data/DbBootstrapper.cs:33 | C2 | 4
F7 | Patients | Duplicate patient detection on save | Medicines have a unique SearchKey with a database constraint behind it; patients have nothing equivalent, so the same child can be registered repeatedly. | src/Pharma.Data/OpdService.cs:85 | C2 | 4
F8 | Inventory | Expiry write-off and distributor-return workflow | The Expiring Soon report already computes returnable sealed packs versus loose units to write off, but offers no action to record either. | src/Pharma.Core/Entities.cs:332 | C2 | 3
F9 | Purchasing | Purchase orders / reorder from Low Stock | Low Stock identifies what has fallen below reorder level but nothing can be raised from it. | src/Pharma.Data/PharmacyService.cs:889 | C2 | 2
F10 | Purchasing | Supplier ledger and payables | StockEntry.NetAmount and DiscountPercent are stored on the entity but never populated or reported; there is no view of what is owed to whom. | src/Pharma.Core/Entities.cs:364 | C2 | 2
F11 | Counter | Barcode scanning | Every counter line is found by typing. Barcode entry would cut both time and mis-picks. | src/Pharma.App/Views/SaleView.xaml | C2 | 5
F12 | Patients | Send receipt or prescription by SMS / WhatsApp | Documents can only be printed or previewed as PDF today. | src/Pharma.App/Printing/PrintService.cs | C2 | 2
F13 | Billing / Tax | IGST / inter-state billing | CGST+SGST only. Documented as a deliberate v1 scope decision - log only if you want to revisit it. | src/Pharma.Core/GstCalculator.cs (class comment) | C2 | 5